## Summary
SmartDoc 2.0 -- master tracker
Branch feature/smartdoc-2.0 · source docs/SMARTDOC_2_0_TRACKER.json · updated 2026-10-14
Status | Tasks | Roadmap milestones
BACKLOG | 7 | 5
READY | 0 | 1
IN_PROGRESS | 0 | 0
BLOCKED | 0 | 0
TESTING | 0 | 0
VERIFIED | 7 | 2
DONE | 4 | 1
Total | 18 | 9
Tasks done or verified | 61.11%
Open P0 tasks | 0
Open bugs | 2
Statuses: BACKLOG, READY, IN_PROGRESS, BLOCKED, TESTING, VERIFIED, DONE. Edit the JSON source and rebuild.

## Roadmap
Phase | Milestone | Objective | Status | Dependencies | Target outcome
P0 | Audit, baseline, branch, tracker | Know the real state; plan; isolate 2.0 | DONE |  | Spec, decisions, tracker, branch, first milestone defined
P1 | Design system and app shell | Tokens, typography, primitives, states, responsive shell | VERIFIED | P0 | Every screen built from shared tokens and primitives
P2 | Auth UI, Dashboard, New Project | Approved screens 1-3 on existing auth and data | VERIFIED | P1 | Sign in/up, project gallery, project-type chooser
P3 | Document creation workflow | Add content -> analyze -> review structure -> style -> editor | READY | P2 | Screens 4-6 on the existing import/format backend
P4 | Editor foundations | New editor layout, selection model, contextual toolbar, properties, autosave | BACKLOG | P1 | Screen 7 for Document Mode
P5 | Free Design foundations | Canvas kind, elements, drag/resize, layers, alignment, sizes | BACKLOG | P4 | Editable canvas projects saved and exported
P6 | Templates and AI design assistance | Template library for both kinds; AI proposals with approval | BACKLOG | P4, P5 | Editable templates; approve/reject AI changes
P7 | Translation | Translate panel; segment pipeline; review; save as new; overflow warnings | BACKLOG | P4 | Structure-preserving translation with review
P8 | Integration, hardening, release readiness | Regression, security, a11y, responsive, compatibility with 1.x data | BACKLOG | P2-P7 | An approvable release candidate

## Tasks
Task ID | Phase | Category | Title | Description | Priority | Status | Dependencies | Acceptance criteria | Owner | Branch | Commit | Preview deployment | Test result | Last updated | Notes
S2-001 | P0 | PROCESS | Audit repository, deployment and trackers | Git state, branches, Vercel project and deployments, 1.x tracker and docs, frontend/editor inventory. | P0 | DONE |  | Baseline recorded in SMARTDOC_2_0_SPEC.md section 2 | Claude | feature/smartdoc-2.0 |  |  | n/a (audit) | 2026-10-14 | HEAD 327e22e; production dpl_HxSobnp5... (4c8fdca); candidate dpl_322ED... (f644146) awaiting promote approval
S2-002 | P0 | PROCESS | Create the SmartDoc 2.0 branch | feature/smartdoc-2.0 from 327e22e, pushed; Preview builds from it. | P0 | DONE | S2-001 | Branch on origin; a READY preview of it | Claude | feature/smartdoc-2.0 | 937d11a | dpl_Bb5PUC2q963bMZmhGaz3bfb44Rb6 (READY); branch alias smartdoc-git-feature-smartdoc-20-drajeto.vercel.app | Preview READY | 2026-10-14 | Branch alias always serves the newest preview of feature/smartdoc-2.0 (behind Vercel Authentication)
S2-003 | P0 | PROCESS | Specification, decisions, roadmap, session state | SMARTDOC_2_0_SPEC/DECISIONS/ROADMAP/PROGRESS/SESSION_STATE.md | P0 | DONE | S2-001 | Files committed; next session can resume from them | Claude | feature/smartdoc-2.0 | 937d11a |  | n/a (docs) | 2026-10-14
S2-004 | P0 | PROCESS | Excel master tracker and its builder | JSON source + tools/smartdoc2/build_tracker.py -> formatted xlsx (filters, frozen headers, conditional formatting, summary formulas). | P0 | DONE |  | xlsx builds and recalculates with 0 formula errors | Claude | feature/smartdoc-2.0 | 937d11a |  | Builder + Excel recalc: 19 formulas, 0 errors; summary values checked | 2026-10-14 | tools/tracker/excel_recalc.py now recalculates any workbook; 1.x value checks only on the 1.x tracker
S2-010 | P1 | DESIGN | Design tokens and Inter font | Colour, radius, shadow, spacing tokens in globals.css @theme; Inter (Latin + Cyrillic) via next/font; light theme first. | P0 | VERIFIED | S2-002 | Tokens used by the new primitives; build passes; Cyrillic renders in Inter | Claude | feature/smartdoc-2.0 | eb69d40 | dpl_4KbNxArvRLBNuJARviMwh5Mj8bys (READY) | tsc, eslint, next build; Playwright visual spec unchanged (editor fonts untouched); Cyrillic seen in Inter locally | 2026-10-14
S2-011 | P1 | DESIGN | UI primitives | components/ui: Button (primary/secondary/ghost/danger, sizes, loading), TextField (label, hint, error), Card, Logo, Spinner, EmptyState, ErrorState. | P0 | VERIFIED | S2-010 | Unit tests for states and accessibility (labels, aria-invalid, focus) | Claude | feature/smartdoc-2.0 | eb69d40 | dpl_4KbNxArvRLBNuJARviMwh5Mj8bys (READY) | ui.test.tsx 7 passed; Vitest 374 | 2026-10-14
S2-012 | P2 | UI | Login / Registration screen (screen 1) | Split layout: brand panel + form card; sign in / create account; validation and server errors; no social login, no reset promise while e-mail is off; existing auth API and session cookie unchanged. | P0 | VERIFIED | S2-011 | Existing AuthForm tests and Playwright auth specs pass; seen in the browser on a throwaway local server; preview builds | Claude | feature/smartdoc-2.0 | eb69d40 | dpl_4KbNxArvRLBNuJARviMwh5Mj8bys (READY) | Playwright auth/visual/CSP/documents 17 passed; local browser: sign in, create account, wrong-password message, 375 px | 2026-10-14 | Also forgot/reset password and address confirmation pages on the same layout. Owner's look at the preview pending.
S2-013 | P1 | DESIGN | Application shell | Top bar + left navigation (Home, Projects, Templates, Settings) + content area, responsive (drawer under md). | P1 | VERIFIED | S2-011 | All signed-in pages render inside it; keyboard navigation; 375 px works | Claude | feature/smartdoc-2.0 | 1003d53 | dpl_47bxa2UQMU5Q52ceD4T2uDAWUVrn (READY, 1003d53) | AppShell.test.tsx 4; Vitest 378; Playwright full 57 + accessibility/auth 11 after fixes; local browser 1280 px and 375 px (drawer, Escape, no horizontal overflow) | 2026-10-14 | Editor, compare, create wizard and public page keep AppHeader (restyled) until their own milestones
S2-014 | P2 | UI | Dashboard (screen 2) | Create Project, recent projects gallery with thumbnails, search, type/last-edited, templates and AI entry, empty/loading/error states. | P1 | VERIFIED | S2-013 | Existing documents listed; search works; states tested | Claude | feature/smartdoc-2.0 | 9ed36a6 | dpl_2rXqkcjNs6Ev8c5ngf3BcFXfornz (READY, 9ed36a6) | Dashboard.test.tsx 7 (gallery, search debounce, empty/no-match/error/loading, describe -> New Project, Bulgarian); e2e: empty dashboard -> New Project, search by title; local browser EN/BG 1280 px | 2026-10-14 | Thumbnails are a drawn page (real first-page previews: S2-018). Search uses the existing /documents?q=.
S2-015 | P2 | UI | New Project (screen 3) | Project-type chooser + 'Describe what you want to create...' input; routes Document types to Add Content, Free Design types to canvas size choice. | P1 | VERIFIED | S2-013 | Each type leads somewhere real; nothing pretends to work | Claude | feature/smartdoc-2.0 | 9ed36a6 | dpl_2rXqkcjNs6Ev8c5ngf3BcFXfornz (READY, 9ed36a6) | NewProject.test.tsx 18 (keyword suggestions EN/BG, whole-word short keys, real hrefs, canvas types disabled, description from the dashboard, Bulgarian); e2e: suggestion + Document -> /new; signed-out redirect | 2026-10-14 | /projects/new; types without a flow are labelled Coming soon (canvas: P5). Suggestion is a keyword match and says so (not AI).
S2-020 | P3 | UI | Add Content / Structure Review / Style screens (4-6) | Rebuild the create wizard as the approved 3-step flow on the existing import + structure + format APIs; structure review edits (rename, level, reorder, reclassify). | P1 | BACKLOG | S2-015 | TXT/DOCX/PDF/paste reach the editor through review; original content preserved | Claude | feature/smartdoc-2.0 |  |  |  | 2026-10-14 | Structure review editing may need a backend endpoint (additive)
S2-030 | P4 | EDITOR | Editor layout v2 (screen 7, Document Mode) | Left (outline/pages/elements), center canvas, top contextual toolbar, right properties, collapsible AI panel; reuses the existing Tiptap editor modules. | P1 | BACKLOG | S2-013 | Existing editor tests and Playwright editor specs pass | Claude | feature/smartdoc-2.0 |  |  |  | 2026-10-14
S2-040 | P5 | EDITOR | Canvas document kind and model | kind=canvas in documents.data with schema_version; adapter: old documents = flow; validation on the backend. | P1 | BACKLOG | S2-030 | Round-trip tests; old documents unaffected; no schema migration | Claude | feature/smartdoc-2.0 |  |  |  | 2026-10-14 | D-004, D-006
S2-060 | P6 | AI | AI proposal framework | Proposal = patch against a revision; preview/diff; accept -> revision; reject -> nothing. | P1 | BACKLOG | S2-030 | Rejecting leaves the saved document byte-identical (test) | Claude | feature/smartdoc-2.0 |  |  |  | 2026-10-14 | D-008
S2-070 | P7 | TRANSLATION | Translate panel and review | Scope (selection/element/page/document), languages (auto-detect, BG/EN first), preview, side-by-side compare, save as new. | P1 | BACKLOG | S2-030 | DOCX fidelity tests on representative documents; overflow warnings | Claude | feature/smartdoc-2.0 |  |  |  | 2026-10-14 | Provider: D-007
S2-016 | P2 | I18N | Bulgarian / English interface (D-010) | Typed dictionaries (en source, bg checked), cookie smartdoc_locale (1 year), first visit from Accept-Language (bg -> BG, else EN), switch in Settings and on sign-in pages, <html lang>, Intl relative times; independent of document language and Translate. | P0 | VERIFIED | S2-011 | Both languages render; choice persists across reloads; parity of keys and placeholders tested | Claude | feature/smartdoc-2.0 | 9ed36a6 | dpl_2rXqkcjNs6Ev8c5ngf3BcFXfornz (READY, 9ed36a6) | i18n.test.tsx 19 (negotiation, cookie precedence, key/placeholder parity, switch + cookie + refresh, fallback); e2e: bg-BG browser starts in BG, switch to EN survives reload, Settings switch survives reload | 2026-10-14 | Preference per browser (cookie), not per account: an account-level setting would need a schema change (D-004).
S2-017 | P2 | I18N | Move the remaining 1.x screens onto the dictionaries | Editor, create wizard, templates, documents list, billing, account settings content, compare, password reset forms: their English strings into en/bg. | P1 | BACKLOG | S2-016 | No hard-coded interface English left in those screens (a grep test); both languages rendered in their tests | Claude | feature/smartdoc-2.0 |  |  |  | 2026-10-14 | Until then those screens show English in Bulgarian mode.
S2-018 | P2 | UI | Real project thumbnails | A small rendering of a project's first page for the gallery (generated on save or on demand, stored as an asset). | P2 | BACKLOG | S2-014 | Cards show the real first page; no cost on every list request | Claude | feature/smartdoc-2.0 |  |  |  | 2026-10-14 | Needs a storage decision (assets) -- additive, no schema change if kept as an asset of the document.

## Bugs
Bug ID | Severity | Reproduction steps | Expected result | Actual result | Status | Fix commit | Verification
B-001 | High | Production (4c8fdca): upload a DOCX with a picture; wait > 5 min idle; reopen | Picture shown | Production stores files on the container's disk until the promote with STORAGE_BACKEND=s3 (settings added 2026-10-13, not yet deployed) | BLOCKED | a07ebd3 / promote of f644146 | Verified on Preview (REL-005); production needs the approved promote
B-002 | Low | Open a document created on Production before the S3 settings, with pictures | Pictures shown | Pictures were on a replaced instance's disk: missing | BACKLOG |  | Not fixable retroactively; owner decided to keep the data (REL-020)
B-003 | Low | Phone width, open the menu drawer | Logo mark in its blue-purple gradient | Mark colourless: every logo copy used the same SVG gradient id; the first copy (hidden sidebar) defined it | VERIFIED | 1003d53 (gradient in CSS) | Seen in the local browser after reload
B-004 | Medium | Open Projects, Templates or Plan and billing inside the new shell; run axe | No serious violations | Grey zinc-500 text under 4.5:1 on the shell background | VERIFIED | 1003d53 (text-muted token) | Playwright accessibility spec passes
B-005 | Medium | Local (SQLite) API: create a project, look at the dashboard from Sofia (UTC+3) | Edited just now | Edited 3 hours ago: a time without a zone was read as local time | VERIFIED | 9ed36a6 (parseServerTime: no zone = UTC; also lib/format.ts) | i18n.test.tsx case; seen in the local browser

## Tests
Test ID | Area | Scenario | Environment | Result | Evidence | Date
T-001 | Backend | Full pytest suite | Local | PASS 2599 / 11 skipped | 1.x tracker RUN-0309 (b5f8142) | 2026-10-13
T-002 | Frontend | Vitest | Local | PASS 368 | RUN-0306 | 2026-10-13
T-003 | E2E | Playwright Chromium (production build, throwaway API) | Local | PASS 59 / 1 skipped | RUN-0307 | 2026-10-13
T-004 | Storage | TXT, DOCX with picture, export, reopen after idle | Preview 3302c48 | PASS | Owner's browser test + Supabase storage logs | 2026-10-13
T-005 | Frontend | Vitest full | Local | PASS 378 | 1003d53 | 2026-10-13
T-006 | E2E | Playwright full (Chromium, production build) | Local | 57 passed, 2 failed -> fixed; accessibility + auth 11 passed | 1003d53 | 2026-10-13
T-007 | UI | Sign in / create account / error / 375 px; shell 1280 + 375 px, drawer | Local throwaway servers | PASS | Browser pane screenshots | 2026-10-13
T-008 | Deploy | 2.0 preview builds | Vercel Preview | READY: 937d11a, eb69d40 | dpl_Bb5P..., dpl_4KbN... | 2026-10-13
T-009 | Frontend | Vitest full | Local | PASS 422 | 9ed36a6 | 2026-10-14
T-010 | E2E | Playwright full incl. smartdoc2.spec.ts (5 new) | Local (production build) | PASS 64 / 1 skipped | 9ed36a6 | 2026-10-14
T-011 | UI | Dashboard + New Project in English and Bulgarian, 1280 px; language switch from Settings | Local throwaway servers | PASS (2 layout issues + time-zone bug found and fixed) | Browser pane screenshots | 2026-10-14
T-012 | Deploy | 2.0 preview builds | Vercel Preview | READY: 1003d53, 9ed36a6 | dpl_47bx..., dpl_2rXq... | 2026-10-14

## Decisions
Decision ID | Topic | Approved decision | Date | Impact | Related tasks
D-001 | Branch | feature/smartdoc-2.0 from 327e22e | 2026-10-13 | All 2.0 work | S2-002
D-002 | Isolation | Branch + its own Preview; Production unchanged without approval | 2026-10-13 | Releases | S2-002
D-003 | Visual direction | Approved Canva-inspired original design system; seven screens | 2026-10-13 | P1-P6 | S2-010..S2-030
D-004 | Data safety | Preview shares the production DB/bucket: no schema change or destructive operation without approval; new models in JSONB with kind+schema_version | 2026-10-13 | P3-P7 | S2-040
D-005 | Font | Inter (Latin + Cyrillic) via next/font | 2026-10-13 | P1 | S2-010
D-006 | Document vs Free Design | Two kinds (flow, canvas) in one store; paragraphs never free boxes | 2026-10-13 | P4-P5, P7 | S2-040
D-007 | AI / translation providers | Use existing adapters; paid keys/providers need approval | 2026-10-13 | P6-P7 | S2-060, S2-070
D-008 | AI approval model | Proposal -> preview -> accept/reject; reject changes nothing | 2026-10-13 | P6-P7 | S2-060
D-009 | Translation | Dedicated panel; segment-level; new document by default; overflow warnings | 2026-10-13 | P7 | S2-070
D-010 | UI language | Interface in Bulgarian and English: first visit from the browser language (bg -> BG, else EN); manual switch in Settings (and sign-in pages); remembered per browser (cookie, 1 year); independent of document language and Translate; centralised dictionaries; tests for both languages and persistence | 2026-10-14 | All screens | S2-016, S2-017
D-011 | Tracker | JSON source + builder -> SMARTDOC_2_0_MASTER_TRACKER.xlsx | 2026-10-13 | Process | S2-004

## Release Readiness
Requirement | Preview status | Production status | Blocking issue | Approval required
1.x hardening promote (f644146) with S3 storage settings | VERIFIED (storage, fra1) | Settings added, not deployed | Promote not approved | Yes -- owner
SENTRY_DSN in Production | n/a | Missing | Owner adds it | Owner action
Real e-mail + password recovery | Disabled honestly | Disabled honestly | No sending domain | Yes -- domain/provider
Cross-account isolation verified live | Local security suite passes | Not verified live | Owner's two-account check | Owner action
Public sign-up | Behind Vercel Authentication | Behind Vercel Authentication | E-mail + isolation above | Yes -- owner
SmartDoc 2.0 release | P1 + P2 done (design system, shell, sign-in, dashboard, new project, BG/EN) | Not started | Phases 1-8 | Yes -- owner